## Hoja1
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
Task | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
| Proyect Scope |  |  |  |  | Data Process |  |  |  |  | Data Analytics |  |  |  |  | Final Demo
Planteamiento, alcance y tecnologías
Establecer KPI's
Definir entregables
Definir datasets
EDA preliminar
Validación de datos
Diseño de modelo ER
Creación Data Warehouse
Carga incremental y automatización
Diseño de reportes
Dashboard
Implementación de modelos de ML
Prepaparación de la demo final
Entregable final
Presentación de la demo

## Hoja2
PLANTILLA DE DIAGRAMA DE GANTT
| PROYECT NAME | HOUSE MARKET
| NAME OF ENTERPRISE | NEW-DATA CONSULTING
| DATE | Monday November 14th 2022
[9 empty] | PHASE ONE |  |  |  |  | PHASE TWO |  |  |  |  | PHASE THREE |  |  |  |  | PHASE FOUR
|  | TASK | MEMBER | START | ESTIMATED | ACTUAL | DURATION | TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
| IDENTIFICADOR | TITULE | OF CHARGE | DATE | END DATE | END DATE | DAYS | PROGRESS PCT | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| 1 | Phase 1. Proyect Scope | [6 empty] | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9
| 1.1 | Approaac and Scope | TEAM | 2022-11-14 | 2022-11-15 | 2022-11-16 | 3 | 100% | bar: WEEK 1 M 14 to WEEK 1 T 15
| 1.1 | Schedule and solution | MV - KC | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2 | 100% | bar: WEEK 1 T 15
| 1.2 | Set KPI's | JC - EH | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2 | 100% | bar: WEEK 1 T 15
| 1.3 | Data validation | TEAM | 2022-11-16 | 2022-11-17 | 2022-11-17 | 2 | 100% | bar: WEEK 1 W 16
| 1.4 | Preliminary EDA | TEAM | 2022-11-16 | 2022-11-18 | 2022-11-18 | 3 | 100% | bar: WEEK 1 W 16 to WEEK 1 T 17
| 1.5 | Progress report and presentation | TEAM | 2022-11-18 | 2022-11-18 | 2022-11-18 |  | 100% | bar: WEEK 1 F 18
| 2 | Phase 2. Data Process
| 2.1 | Data validation | TEAM | 2022-11-21 | 2022-11-22 | 2022-11-22 | 2 | 100% | bar: WEEK 2 M 21
| 2.2 | Data Warehouse creation | JC | 2022-11-22 | 2022-11-23 | 2022-11-23 | 2 | 100% | bar: WEEK 2 T 22
| 2.3 | ER model definition | KC | 2022-11-22 | 2022-11-23 | 2022-11-23 | 2 | 100% | bar: WEEK 2 T 22 to WEEK 2 W 23
¦ | 2.4 | Pipelines | MV | 2022-11-22 | 2022-11-24 | 2022-11-24 | 3 | 100% | bar: WEEK 2 T 22 to WEEK 2 T 24
| 2.5 | DW automation | KC | 2022-11-22 | 2022-11-24 | 2022-11-24 | 3 | 100% | bar: WEEK 2 T 22 to WEEK 2 T 24
| 2.6 | Progress report and presentation | TEAM | 2022-11-25 | 2022-11-25 | 2022-11-25 |  | 100% | bar: WEEK 2 F 25
| 3 | Phase 3. Data Analytics
| 3.1 | Data Analysis | KC-EH | 2022-11-28 | 2022-11-30 | 2022-12-04 | 6 | 100% | bar: WEEK 3 M 28 to WEEK 4 M 5
| 3.2 | ML model implemantion | MV | 2022-11-28 | 2022-12-01 | 2022-12-04 | 6 | 100% | bar: WEEK 3 M 28 to WEEK 4 M 5
| 3.3 | ML model adjust | JC | 2022-11-28 | 2022-12-02 | 2022-12-04 | 6 | 100% | bar: WEEK 3 M 28 to WEEK 4 M 5
| 3.4 | Dashboard | KC -EH | 2022-11-28 | 2022-12-03 | 2022-12-04 | 6 | 100% | bar: WEEK 3 M 28 to WEEK 4 M 5
| 3.5 | Progress report and presentation | TEAM | 2022-12-02 | 2022-12-02 | 2022-12-02 |  | 100% | bar: WEEK 3 F 2
| 4 | Phase 4. Final Demo
| 4.1 | Demo final preparation | MV-EH | 2022-12-05 | 2022-12-07 | 2022-12-07 | 2 | 100% | bar: WEEK 4 M 5 to WEEK 4 T 6
| 4.2 | Final delivery | JC -KC | 2022-12-05 | 2022-12-07 | 2022-12-07 | 2 | 100% | bar: WEEK 4 M 5 to WEEK 4 T 6
| 4.3 | Demo presentation | TEAM | 2022-12-06 | 2022-12-07 | 2022-12-07 | 1 | 100% | bar: WEEK 4 W 7
|  | EH : | Estanislao José Haquin
|  | JL : | Julia Caro
|  | KC : | Karen Cruz
|  | MV : | Marlene Giuliana Vigil